## Definitions
Definitions of Control and Critical Control
No
Sourced from Hassall & Harris (2017). Risk Controls Knowledge: Determining leading practice from case study analysis. ACARP report no C25036. Available at
| Yes |  | No |  | Yes | No | Yes | www.acarp.com.au/reports.aspx
And QGN 35 The integration of Critical controls into PHMPs for Coal mines in Queensland
ICMM Guide to Critical Controls 2026
No
| Yes |  |  |  | Yes |  | Yes
Yes
Yes
Yes
No
Is it of itself a an act, object, or combinationof acts and objects?
Is it an activity/item or source of informaiton that maximises the health/ minimises erosion of the control?
Is it an in-field check to ensure that the control is implemented
Does it of itself directly prevent an hazard or mitigate an unwanted outcome?
Is the activity/item or source of information specifable, obserable an auditable?
Is it an activity that determines if a control is healthy / functioning as required?
Is the required performance specifiable, measureable, and auditable?
A CONTROL
A SUPPORTING ACTIVITY
A VERIFICATION ACTIVITY
START
NOT PART OF A CONTROL SYSTEM
Does the absence or failure of this control significantly increase the risk of a fatality?
Is the control commonly assocated with previous incidents?
Would additional verification by management help ensure performance of the control?
CRITICAL CONTROL
OTHER CONTROL

## Scope
Company
Site |  | Revision 1 | Revision 2
Risk Assessment Number (If applicable)
Risk Assessment Name
Risk Owner
Risk Coordinator / Facilitator
Dates of Assessment
SCOPE OF ASSESSMENT
Category | In Scope | Out of Scope
Objective: Purpose of the risk management activity being undertaken
Hazards: Hazardous chemicals, energies and biological agents that could impose harm
Scenarios: Known risk scenarios that need to be considered
People: People involved in management of the risk and people potentially impacted if risks are not managed
Locations: Locations or areas where the risk exists or that could be impacted by the risk event if it occurs
Equipment: Equipment and plant exposed to the risk and associated with managing the risk
Activities: Activities include operations, maintenance, startup, shutdown, normal and abnormal tasks and functions that could impact or be impacted by the risk
Timeframes: To capture time considerations (e.g. the times of the day or days of year) that risk needs to be managed plus other considerations such as shift changes and how far into the future is being considered
External considerations: Known weather and climate related conditions (e.g. heatwave, tsunami, bush fire, earthquake). Any fauna or flora issues (e.g. dangerous wildlife). External human/societal considerations (e.g. cyber, political, social)
Other assumptions: Captures other information and issues that have been considered

## Attendees
Attendees |  |  |  | Day 1 | Day 2 | Day 3
# | Name | Position | Company (if applicable) | 2020-01-01 | 2020-01-02 | 2020-01-03
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## References
Legislation and Standards
AS/NZS 4326 The Storage and Handling of Oxidising Agents
WHS Act and Regulations
Credible Initiator / Scenario | Relevant Incident Evidence | Lesson Learned / Justification for Inclusion | Reference Links

## Risk Assessment
RISK ASSESSMENT TITLE:
ID | Hazard | Risk Description There is a chance that… | Risk Cause Because of… | Potential Consequences / Impacts Which could lead to… | Main Category | Consequence | Likelihood | Initial Risk Level | Existing (Proposed) Controls | Consequence | Likelihood | Residual Risk Level | Risk Treatment Options | Treat or Accept Risk? | Risk Treatment Plan Actions
1 | Chemical | LOC of IBC Contents | Damaged valve | Loss of contents to bunded area. Chemical burns to personnel. Cmall financial cost | Safety | 2 - Moderate | 2 - Unlikely | L |  | 2 - Moderate | 2 - Unlikely | L
2 | Chemical | LOC of IBC Contents | Punctured by forlift tyne | Loss of contents to unbunded area and down drains. Chemical burns to personnel. Small financial cost. | Safety | 2 - Moderate | 2 - Unlikely | L |  | 2 - Moderate | 2 - Unlikely | L
3
4
5
6
7
8

## Risk Matrix
| Impact to Company or contracting personnel | Natural environment | Community damage/impact/social/cultural heritage | Financial impact (eg. due to loss of revenue, business interruption, commodity trading, asset loss) | Damage to reputation, services interruption, customer interruption | Breach of law or criminal prosecution or civil action (eg. OHS, environment, industrial relations, trade practices, industry acts) | 1 - Remote | 2 - Unlikely | 3 - Possible | 4 - Likely | 5 - Almost Certain | Client Consequence | Client Liklig=hood | Description
5 - Critical | 1+ fatalities or serious irreversible disability (>30%) to multiple persons (<10). | Major offsite release or spill, significant impact on highly valued species or habitats to the point of eradication or impairment of the ecosystem. Widespread long-term impact. | Community fatality. Significant breakdown of social order. Ongoing serious social issue. Major irreparable damage to highly valuable structures/ items of cultural significance. | Client Driven numbers | Negative media national for 2 days or more. Significant public outcry. Severe degradation of services to customers up to 1 month or >5,000 customer days | Very significant fines and prosecutions. Multiple prosecution and fines. | M | H | H | E | E | 5 - Critical | 1 - Remote | 1 REMOTE <1% chance of occurring within the next year. Occurance requires exceptional circumstances. Exeptionally unlikely event in the long term future. Only occur as a 100 year event
4 - Major | Serious permanent injury/ illness or moderate irreversible disability (<30%) to one or more persons. | Offsite release contained or immediately reportable event with very serious environmental effects, such as displacement of species and partial impairment of ecosystem. Widespread medium and some longterm impact. | Serious injury to member of the community, Widespread social impacts. Significant damage to items of cultural significance. |  | Negative national media for 1 day. Individual customers or segments disadvantaged up to 1 week. Customer interruption >500 customer days. NGO adverse attention. | Major breach of regulation and significant prosecution including class actions. | L | M | H | H | E | 4 - Major | 2 - Unlikely | 2 UNLIKELY >5% chance of occurring within the next year. May occur but not for awhile. Could occur within a few years
3 - Serious | Serious reversible/ temporary injury/illness (e.g. lost time >5 days or hospitalisation or Alternate/Restricted Duties > 1 month). | Moderate effects on biological or physical environment and serious short term effect to ecosystem functions. | Media attention and heightened concerns by local community and criticism by NGOs. Ongoing social issues. Permanent damage to items of cultural significance. |  | Negative state media. Heightened concern from local community. Service interruption up to 1 day or > 10 customer days. Criticism by NGOs. | Serious breach of law/regulation with investigation or report to authority with possible prosecution. Performance Infringement Notice (PIN | L | M | M | H | H | 3 - Serious | 3 - Possible | 4 POSSIBLE >10% chance of occurring within the next year. May occur shortly but a distinct probability it won't. Could occur within months to years.
2 - Moderate | Reversible temporary injury/illness requiring Medical Treatment (e.g. lost time <5 days or Alternate/Restricted Duties for < 1 month). | Event contained within site. Minor short term damage to area of limited significance. Short term effects but not affecting ecosystem functions. | Medical treatment injury to a member of the community, Minor adverse local public or media attention and complaints. Minor medium term social impact on local population, mostly repairable. |  | Public concern restricted to local complaints Negative local media. Internal escalation to senior management. Few hours service interruption. Adverse local public attention. | Breach of law/regulation or non-compliance. Minor legal issues, minor litigation possible. | L | L | M | M | H | 2 - Moderate | 4 - Likely | 4 LIKELY >50% chance of occurring within the next year. Balance of probability will occur. Could occur within weeks to months.
1 - Minor | Injury/illness requiring Medical Treatment (no lost time, no Alternate/Restricted Duties), First Aid, Report Only. | Minor consequence, local response. No lasting effects. Low level impacts on biological and physical environment to an area of low significance. | Public concern restricted to local complaints, low level repairable damage to common place structures. |  | Public concern restricted to local complaints. | Local investigation, minor breach of regulation, on the spot fine or technical noncompliance. Prosecution unlikely. | L | L | L | L | M | 1 - Minor | 5 - Almost Certain | 5 ALMOST CERTAIN 99% chance of occurring within the next year. Impact is occurring now. Could occur within days to weeks.
| 5 - Critical | [5 empty] | 1 REMOTE <1% chance of occurring within the next year. Occurance requires exceptional circumstances. Exeptionally unlikely event in the long term future. Only occur as a 100 year event | 2 UNLIKELY >5% chance of occurring within the next year. May occur but not for awhile. Could occur within a few years | 4 POSSIBLE >10% chance of occurring within the next year. May occur shortly but a distinct probability it won't. Could occur within months to years. | 4 LIKELY >50% chance of occurring within the next year. Balance of probability will occur. Could occur within weeks to months. | 5 ALMOST CERTAIN 99% chance of occurring within the next year. Impact is occurring now. Could occur within days to weeks.
4 - Major
3 - Serious
2 - Moderate
1 - Minor
Community
Environment
Financial
Health
Legal
Reputation
Safety